## Sheet 0
PCREEE 2021 CALENDAR OF EVENTS
(as of 15 Nov 2021)
Divisional Business Plan Objective: Quality Technical Assessments in Georesources and Energy
Result 2.2: PICTs supported with technical assistance for improved minerals management and energy efficiency and strengthened sustainable and renewable energy industry
Indicator 2.2.5: Evidence of Increased involvement of the private sector in renewable energy and energy efficiency initiatives through PCREEE in PICTs
Baselines: There is no fully functional, staffed and resourced regional energy entity focusing on the private sector; No targeted training and research programme for the private sector;
No targeted and centralised on-line data and info for the private sector; Lack of new local sustainable energy businesses registered in PICs; Lack on new PPAs signed in the PICs;
Lack of targeted national and regional funds to support private sector investments in Renewable Energy (RE) & Energy Efficiency (EE);
Absence of a regular forum for private sector and investors interactions with governments, power utilities and transport authorities
| PCREEE Business Plan |  |  |  | FESRIP Priority Areas
Programme 0 (P0). General Administration and Governance
| Programme 1 (P1). RE&EE Business Start-Up and Entrepreneurship Support |  |  |  | Energy Sector Finance & Cooperation
| Programme 2 (P2). RE and EE for Sustainable Mobility |  |  |  | Low carbon transport energy
| Programme 3 (P3). RE mini-grids |  |  |  | Sustainable electric power development
| Programme 4 (P4). Energy Efficiency Investment |  |  |  | Improved Energy Efficiency
| Event | Recipient | Programme Area Support | Start Date | End Date | Lead Officer | Notes | Update 15 November 2021
| PCREEE Fabrication and installation of VCF | Regional | P0 | Oct | Dec | M-PCREEE / PDO | Need these more given more reliance on virtual deliveries because of the COVID restrictions. | Construction is curently underway. VCF andfurnishing contracts have been signed.
| Finalise PCREEE Business Plan and sign Contribution Agreement with the Austrian Development Agency | Regional | P0 | Jan | March | M-PCREEE |  | Completed. BP launched 27 April. CA with ADA signed 17 Aug and first tranche [300k] payment received.
| Prepare PCREEE July - Dec 2020 Progress Report for UNIDO | Regional | P0 | Jan | Feb | M-PCREEE, Finance Officer (Suva) & PA | Report will include an updated Asset Register (PA) and will trigger the signing of a Phase 2 MoU with UNIDO. | Completed
| Strategic Evaluation of the NZ MFAT Energy Programme | Regional | P0 | Jan | May | M-PCREEE | Consultancy with Coffey International. | A resource mobilisation effort. Completed and full payment received.
| Develop and facilitate volunteer recruitments – Entrepreneurship and Business Mentor, Graphic Designer, etc | Regional | P0 | Feb | June | PDO | Recruitment of Vounteers put on hold given difficulty of their remote deliveries. Focus on recruting ICCs. | Completed. AVI [Blake Calogero] completed assignment in Aug. PIEP started 25 Oct. Recruitment of regional and national consultants in CI, SI and PNG underway.
| Prepare PCREEE 4th Year Progress Report & First Operation Phase report | Regional | P0 | March | April | PDO |  | Completed 4th annual report but FOP report due in Sept.
| PCREEE 4th Anniversary (including development and launch of new initiatives and awareness materials) | Regional | P0 | April | April | PDO | Development, design and printing of PCREEE 4th Progressive Report | Completed
1 | 6th PCREEE Steering Committee Meeting | Regional | P0 | Nov | Nov | PDO | To be conducted back-to-back with a EV training on 29 Nov. | Confirmed for 30 Nov.
| 2021 Wrap Up & Reporting | Regional | P0 | Dec | Dec | M-PCREEE | December is reserved for whatever activity is left above can be further pushed to December for completion | Amended contract with UNIDO not yet signed. They may demand a FOP [2017-2021] report.
| Regular updates on the Assets Register, finance and payments, etc | Regional | P0 | Jan | Dec | PA |  | On-going.
| Promote PCREEE visibility through a regularly update website | Regional | PO | Jan | Dec | PIEP |  | On-going
| Draft the PCREEE RE & EE Business Start-Ups and Entrepreneurship Support Initiative | Regional | P1 | Feb | March | M-PCREEE | To be laucnhed at the 4th Anniverssary of the PCREEE in April | Completed
| Prepare a bid with One Energy Island and others to design a private sector led regional Facility for RE | Regional | P1 | Jan | Jan | M-PCREEE | Response to a RFP by the NDC Partnership and the Govt of Fiji. | Completed and was unsuccessful
| Support UPNG workshop on PacTVET Levels 3 & 4 | PNG | P1 | Feb | April | Business & Mini-grids Officer | As requested by Manu Rawali on 27 Jan. | Training of Trainers was completed 7 - 11 June
| Support certification and accreditation of national qualifications and training institutes in the Pacific | Tonga, Regional | P1 | Jan | June | BMO | (i) Engage expert to complete Tonga NCSE L3 & L4 for registration (ii) Promote and launch the SIDS Dock on-line training programme https://training.gn-sec.net | RFQ for a Sustainable Energy Instructor in Tonga was launched earlier in Nov.
2 | Conduct SE Investment Forum (including awareness raising) | Honiara, Solomon Islands | P1 | April | April | PDO | Forum will cover all PCREEE programmes and to be conducted jointly with PFAN and others. | Postponed due to DoE's request. Completed IF for Vanuatu on 1 & 2 Sept
| Facilitate establishment of Sustainable Energy Industry Associations in PICs | Honiara, Solomon Islands | P1 | April | April | PDO | Back to back with the SE Investment Forum and follow-ups thereafter | Postponed due to DoE's request. Obvious lack of capacity in SI and now recruting a ICC to assist.
| Support to Vanuatu's GCF SAP on the NGEF | Vanuatu | P1 | Feb | May | PDO | Currently with SPC's CCES for Review | Officially submitted by SPC as AE to GCF in June. GCF comments have been addressed and resubmitted in Nov.
| Conduct National Trainings for private sector on tendering and contract management | Samoa | P1 | May | May | PDO | Palau - March, Samoa - May, Vanuatu - July | Samoa DoE's priority was a SE Awareness event focussing on Evs. Completed on 21 & 22 Oct.
| Support TIST with delivery of SE Qualifications | Tonga | P1 | May | May | BMO | Recruitment and Funding of course instructor for 2nd Semester 2021 | RFQ for a Sustainable Energy Instructor in Tonga was launched earlier in Nov.
| Develop regional mini-grid standards and guidelines | Regional | P1 | Aug |  | PDO | ToR and RFP required | To be discussed with partners on mini-grids
| Conduct desktop study, market research and stocktake on EVs, BEVs and EE in land transport in the PICTs | Regional | P2 | Jan | June | PIEP | To be conducted jointly with the market research and data collection on RE- mini-grids. | On-going by Sione.
3 | Conduct regional training on EE in land transport | Regional | P2 | Aug | Aug | PDO | To be based on the EE in land transport module of the SIDS Dock on-line training programme https://training.gn-sec.net | Planned with ISA, UNIDO, Climate Parliament etc but not progressing. Planning one on EVs with UNIDO and Andrew Campbell on 29 Nov.
| Support PICs to develop funding proposals to address EE in land transport | Regional | P2 | Feb | June | PDO | CTCN launched the Vanuatu RFP SI CTCN proposal is with their NDE to submit Draft Tonga GCF Proposal | Completed Vanuatu and SI, working on Tonga's
4 | Conduct feasibility studies on EVs and Identify feasible EV targets | Regional | P2 | June | Dec | PIEP | Available to the PICTs on a first come first served basis. Two TAs in 2021. | Completed developing leaflet to promote the PEV ReadPro. CTCN is currently doing FS in Vanuatu and SI.
| Regional webinar on solar transport for SIDS, the role of solar in addressing COVID-19 and the productive uses of solar for empowering women , entrepreneurs and the economy | Regional | P2 | March | May | PDO | Jointly with ISA. A series of webinars on the same week covering the role of solar in addressing COVID-19 and the productive uses of solar for empowering women , entrepreneurs and the economy | Not progressing.
| Prepare awareness materials on EE in land transport & Draft a regional EV ProDoc | Regional | P2 | June | Dec | PIEP | ToR & RFP needed | Sione is working on the awareness materials - printed and audio-visual too. ProDoc is dropped.
| Prepare regional awareness materials on EVs | Regional | P2 | March | Oct | PIEP | Requested by Vanuatu & Nauru. Identified need in Samoa. | A draft EV FactSheet and banner was prepared in Sept. Sione is working on this.
| TA to review Energy Roadmaps, LEDS, NDCs, etc to include EE in transport targets, etc | National and Regional | P2 | April | Sept | PDO | Venue to be confirmed. | Participated in the TERM Plus consultations.
| Support the UNIDO-China PV projects in Fiji | Fiji | P3 | Jan | June | Adrien and the Technical Unit team | Evaluation of bids is to be done in Jan | Handled by Adrien and his team in Suva. Contractor has been selected.
5 | Workshop on electrical safety and compliance | Vanuatu | P2 | July | July | PDO | Requested by Vanuatu | Started TEC's radio talkback. Completed BRANTV training in Santo & Vila. Tanna was to be on 25-29 Oct.
| Conduct Technical Training on O&M of Solar mini-grids | Regional | P3 | March | June | BMO | Jointly with ISA, NREL & INES | Planned for 16 - 17 & 19 Nov
| Conduct market research and data collection on RE- mini-grids | Regional | P3 | Jan | June | PIEP | To be conducted jointly with the market research and data collection on EE in land transport & EVs | Started by Sione.
| TA to establish a database and market -based knowledge platform on mini-grids in PICs | Regional | P3 | July | Dec | PIEP | Use the market research data to design the database. | Started by Sione.
6 | Conduct workshop on electrical safety and standards for electrical contractors | PNG | P3 | Aug | Aug | BMO |  | Currently recruiting a ICC in PNG to assist.
| Complete reporting requirements to CTCN on the Tonga EE Master Plan consultancy | Tonga | P4 | Jan | March | M-PCREEE |  | Completed all the reports and received the UNIDO payments
| Review of national EE financing instruments to facilitate greater uptake of EE equipment | Tuvalu & Nauru | P4 | Sept | Dec | PDO | EE financing instruments available in Tuvalu, Nauru and Palau | No support [and interest] from the ground.
| Conduct national trainings on regulation MEPSL for business and government officials | TBC | P4 | Oct | Oct | PDO | For countries with legislation on MEPSL - Vu, Sam, Fiji & SI | Currently being discussed with the Tonga DoE.
Tonga
· Training is key to sustainability and therefore support having the Level 3 & 4 registered and to have local Technical Institutes deliver these courses
· Donor consultation on the TEEMP will be conducted virtually. GEP will be invited to participate
· GEP is happy to comment on the TERM Plus Framework if made available
· DoE needs similar EE in transport support from GEP like in Vanuatu and SI - draft SAP already circulated
· DoE would like GEP support in EE DSM
· DoE would like to see that Energy is well reflected in the awareness materials GEP is developing for the CC Dept
Vanuatu
10.2.3. a. iii) Develop Wiring Safety Act
iv) Review EE Appliances, Equipment & Lighting Products Act
10.2.3. b) Develop Concept Note for RE Generation Bill
10.5.1 vi- vii ) Technical Training for local operations on O&M for RE systems
10.4.1 c- e) procure and install RE systems for BRANTV
10.6.b. a) Develop hybrid electric vehicles (HEV) Policy
b) Market survey on BEV
c) Support Ministry of Internal Affairs and Ministry of Infrastructure to review the draft National Building Code
e) Develop a national EE strategic Plan
Nauru
⁃ PCREE is keen to jointly implement with Midhun and his team, Transport and other Nauru stakeholders some of the capacity building / awareness activities after CTCN TA report on EE on land transport is available. Knowing study is underway and finalizing soon.
⁃ implement identified awareness and promotion initiatives on E mobility and EE on land transport